## Slide 1: Construction Operations End-to-End Process Flows
Project acquisition, material and vendor acquisition, HRIS payroll, and OPEX consolidation — mapped across the four project phases
PROJECT ACQUISITION
PRE-CONSTRUCTION
CONSTRUCTION
POST-CONSTRUCTION
Four phases · four process chains · owners, forms and approval gates defined at every step

## Slide 2: Four process chains run across the four project phases
PROCESS MAP
1 · PROJECT ACQUISITION
2 · PRE-CONSTRUCTION
3 · CONSTRUCTION
4 · POST-CONSTRUCTION
PROJECT ACQUISITION TO CASH
› Notice of award received
› PR raised against budget
› Subcon bidding and awarding
› PO issued
› Contract signing
› Mobilization plan approved
› Billing schedule locked
› 30% downpayment billing
› Progress billing to 100%
› Invoice and official receipt
› Final billing and punchlist
› Retention release
› Close-out documentation
MATERIAL AND VENDOR ACQUISITION
› Vendor and subcon accreditation
› RFQ to three vendors
› Bid tabulation and award
› BOM converted to PR
› Price agreements signed
› Delivery schedule set
› PO release and delivery
› Receiving, inspection, issuance
› Three-way match to payment
› Final reconciliation
› Warranty turnover
› Vendor scorecard
HRIS: PAYROLL AND TIMELOGS
› Manpower plan and rates approved
› Onboarding and 201 file
› Biometric enrollment
› Cost center assignment
› Daily timelogs and OT approval
› Payroll run and disbursement
› Labor cost posted to project
› Demobilization
› Final pay and clearance
OPEX CONSOLIDATION
› OPEX budget allocated per project
› Opening balances and petty cash
› Chart of accounts mapped
› Expense capture and coding
› Monthly consolidation
› Budget versus actual review
› Final OPEX close
› Project profit and loss
Each cell is a gated step: no step starts without the approved input from the step before it.

## Slide 3: Project acquisition runs seven gated steps from award to first collection
PHASE 1 · PROJECT ACQUISITION
1 PROJECT AWARDED
› Notice of award received
› Contract reviewed and signed
› Project code and budget opened
Signed contract, NTP, project code
Business Dev / PMO
2 PURCHASE REQUISITION
› Scope broken into BOM
› PR raised per cost code
› Budget availability checked
Approved PR, budget clearance
Site Engineer / Procurement
3 VENDOR / SUBCON AWARD
› RFQ to accredited list
› Three quotes tabulated
› Technical and cost evaluation
Bid tabulation, notice of award
Procurement / Technical
4 PO CREATION
› PO raised from awarded bid
› Terms, taxes, delivery dates set
› Countersigned by vendor
Approved PO, subcontract
Procurement / Finance
5 OPERATIONS MOBILIZATION
› Site setup and permits secured
› Manpower deployed and enrolled
› Equipment and materials staged
Mobilization checklist
Operations / HR
6 PROGRESS BILLING
› 30% downpayment billed
› Accomplishment billing to 100%
› Retention withheld per contract
Billing form, accomplishment report
QS / Finance
7 INVOICE AND RECEIPT
› Sales invoice issued on approval
› Official receipt on collection
› AR aging monitored weekly
Sales invoice, official receipt
Finance / Accounting
No PO without an approved PR and a tabulated bid.
No mobilization without a countersigned PO.
No billing without a verified statement of accomplishment.
Downpayment of 30% is billed on contract signing; the balance is billed against verified accomplishment, less retention released at close-out.
GATE RULES

## Slide 4: Material and vendor acquisition: from PR to payment in nine steps
PHASE 2–3 · PROCUREMENT CYCLE
1 PURCHASE REQUISITION
› Site raises PR from the BOM
› Quantity, spec and cost code validated
› Budget availability confirmed
Site Engineer
2 CANVASS AND RFQ
› RFQ sent to three accredited vendors
› Specs, lead time and terms fixed
› Quotes returned sealed
Procurement
3 BID TABULATION
› Price, lead time and terms compared
› Abstract of canvass prepared
› Recommendation drafted
Procurement
4 APPROVAL
› Signed per authority matrix
› Sole source needs written justification
› Rejected PRs returned to site
Finance / Management
5 PO ISSUANCE
› PO carries spec, price, delivery date
› Vendor acknowledges in writing
› Downpayment released if required
Procurement
6 DELIVERY AND RECEIVING
› DR checked line by line against PO
› Short or over delivery noted on DR
› Receiving report issued
Warehouse / Site
7 INSPECTION AND QC
› Material inspected against spec
› Rejects returned to vendor on RTV
› Test certificates filed
QC / Technical
8 WAREHOUSE AND ISSUANCE
› Stock card and bin location updated
› Issued to cost code via material slip
› Physical count every month end
Warehouse
9 MATCH AND PAYMENT
› PO, receiving report and invoice matched
› AP voucher raised with tax documents
› Paid on terms; vendor rated
Accounting / Treasury
Controls: three quotes minimum, PO before delivery, no payment without a three-way match. Vendor accreditation is renewed yearly; scorecards on price, on-time delivery and rejection rate drive the accredited list.

## Slide 5: Approval authority and accreditation decide who can buy, from whom, and how fast
Purchase value | Required documents | Approver | Turnaround
Tier 1 — low value | PR, single canvass sheet | Site Engineer, then Procurement Head | 1 working day
Tier 2 — routine | PR, three quotes, abstract of canvass | Procurement Head, then Finance Manager | 2 working days
Tier 3 — major | PR, three quotes, tabulation, spec sheet | Finance Manager, then COO | 3 working days
Tier 4 — capital or subcontract | Full bid package, contract and legal review | President or Board | 5 working days
PHASE 2 · PRE-CONSTRUCTION CONTROLS
ACCREDITATION FILE
› Business registration and tax certificate
› Local permit and tax clearance
› Bank details and authorized signatory
› Shop or plant validation visit
› Insurance and surety bond for subcontractors
› Renewed every twelve months
VENDOR SCORECARD
› On-time delivery rate
› Rejection rate at inspection
› Price against last canvass
› Completeness of documents
› Rated after every PO
› Reviewed quarterly by procurement
REMOVAL TRIGGERS
› Two late deliveries in one quarter
› Rejected volume above five percent
› Falsified documents — immediate removal
› Unresolved warranty claim
› Suspended until cleared by management
Tiers are shown as bands, not amounts — set the peso limits against your own approval matrix before this is issued. Sole-source purchases skip canvassing only with written justification approved one level above the normal approver.

## Slide 6: Billing runs from a 30% downpayment to 100%, then branches to invoice and receipt
PHASE 3 · PROGRESS BILLING AND COLLECTION
30% DOWNPAYMENT
Contract signed and notice to proceed issued
Billing form, signed contract, invoice request
50% PROGRESS
Verified accomplishment reaches 50%
Accomplishment report, joint survey, photos
75% PROGRESS
Verified accomplishment reaches 75%
Accomplishment report, updated S-curve
95% PRE-FINAL
Substantial completion; punchlist issued
Punchlist, draft as-built drawings
100% FINAL
Punchlist cleared and turnover accepted
Certificate of completion, warranty, clearances
Retention of 10% is withheld on every billing and released after the defects liability period.
Billing submitted to client
Client evaluation
approved
returned
SALES INVOICE ISSUED
Invoice raised against the approved billing; tax documents attached and logged in the AR ledger
COLLECTION FOLLOW-UP
AR aging reviewed weekly; unpaid billings escalated to the project manager at 30 days
OFFICIAL RECEIPT ISSUED
OR issued on payment; retention and deductions reconciled; billing closed in the AR ledger
Returned billings go back to the QS for re-measurement and are resubmitted in the next cutoff. The deduction and its reason are logged so the same item is not billed twice.
Billing cutoff is monthly; every submission needs a joint accomplishment survey signed by the client representative before an invoice can be raised.

## Slide 7: HRIS turns daily timelogs into payroll and posted labor cost in nine steps
PHASES 2–3 · HRIS, PAYROLL AND TIMELOGS
1 MANPOWER REQUEST
› Site requests headcount against the approved manpower plan
› Rate band and duration confirmed
Site / Operations
2 HIRING AND ONBOARDING
› Requirements collected and 201 file opened
› Employment contract signed before first shift
HR
3 HRIS ENROLLMENT
› Employee master data and government numbers encoded
› Biometrics enrolled and cost center assigned
HR / IT
4 DAILY TIMELOGS
› Biometric in and out per shift, backed by the site logbook
› Missing logs flagged the same day
Timekeeper
5 VALIDATION AND OT APPROVAL
› DTR validated against the logbook before cutoff
› Overtime and night differential approved in writing
Site Engineer
6 PAYROLL PROCESSING
› Gross pay computed from validated DTR only
› Loans, cash advances and statutory deductions applied
HR / Payroll
7 REVIEW AND APPROVAL
› Payroll register checked by HR, then Finance
› Variance against last cutoff explained per project
HR / Finance
8 DISBURSEMENT
› Bank upload or cash payout with acknowledgment
› Payslips released on release date
Treasury
9 LABOR COST POSTING
› Cost posted to project cost codes
› Feeds OPEX consolidation and project profitability
Accounting
Cutoffs: 1–15 and 16–end of month. DTR closes one day after cutoff; payroll releases three working days later.
No timelog, no pay: unvalidated days are held and paid in the next cutoff once the site certifies them.

## Slide 8: OPEX is consolidated on a fixed monthly calendar, from capture to management report
PHASE 3 · OPEX CONSOLIDATION
DAY 1–25
CAPTURE
Petty cash, fuel, rentals, utilities and site purchases logged daily with receipts
DAY 26
CUTOFF
Submission closes; cash advances liquidated or charged to the next payroll
DAY 27
CODING
Every expense coded to project, cost center and account before entry
DAY 28
VALIDATION
Accounting checks receipts, tax documents and the budget line charged
DAY 29
CONSOLIDATION
Site and head office OPEX rolled up per project and company
DAY 30
BUDGET REVIEW
Budget against actual by cost center; variance above 10% explained in writing
DAY 3–5
REPORTING
OPEX per project, cost per unit of accomplishment, and forecast to completion
WHAT FEEDS THE CONSOLIDATION
› Labor cost from the payroll register
› Materials and subcontracts from AP
› Site petty cash and revolving fund
› Utilities, rentals and permits
› Equipment fuel, repair and depreciation
› Insurance, bonds and IT services
WHAT THE CONSOLIDATION PRODUCES
› OPEX per project against budget
› Cost per unit of accomplishment
› Variance report by cost center
› Cash requirement for the next month
› Input to project profit and loss
› Forecast cost to completion
Control: an expense with no receipt, no cost code, or no budget line is not booked — it is returned to the site the same day and cannot be charged to the project later.

## Slide 9: Close-out is not finished at turnover — it ends when retention is collected and the books are closed
PHASE 4 · POST-CONSTRUCTION
1 SUBSTANTIAL COMPLETION
› Works reach 95% and the client inspects
› Punchlist issued and signed jointly
Project Manager
2 PUNCHLIST CLEARING
› Items closed and re-inspected item by item
› Subcontractor back-charges computed
Site / QC
3 TURNOVER AND ACCEPTANCE
› As-built drawings, manuals and warranties handed over
› Certificate of completion and acceptance signed
PMO / Client
4 FINAL BILLING
› 100% billing with the final accomplishment
› Deductions and back-charges applied before invoice
QS / Finance
5 DEMOBILIZATION
› Manpower cleared and final pay released
› Equipment, tools and IT assets returned and logged
HR / Operations
6 PROJECT CLOSE-OUT
› Retention collected after the defects liability period
› Final project profit and loss issued; scorecards filed
Accounting / PMO
DOCUMENTS TO CLOSE
› As-built drawings and manuals
› Certificate of completion
› Warranty certificates and permits
FINANCIAL CLOSE
› Final billing and collection
› Retention release
› Final project profit and loss
PEOPLE AND ASSETS
› Clearance and final pay
› Equipment and IT asset return
› Vendor and subcon scorecards
A project stays open in the books until retention is collected; the close-out report names who cleared each item and when.

## Slide 10: Every process ends in the same place: the project cost ledger
DOCUMENT HANDOFFS ACROSS THE FOUR CHAINS
PROJECT ACQUISITION
Signed contract
Billing form
Sales invoice
Official receipt
MATERIAL AND VENDOR
Purchase requisition
Purchase order
Receiving report
AP voucher
HRIS AND PAYROLL
Validated DTR
Payroll register
Payslip
Journal entry
OPEX
Receipt and liquidation
Coded expense entry
OPEX schedule
Budget against actual
PROJECT COST LEDGER
Revenue and receivables
Material and subcontract cost
Labor cost
Overhead
Outputs
Project profit and loss
Cost per unit of accomplishment
Cash position and forecast
Handoff rule: every document carries the project code, the cost code and the reference number of the document before it — PR on the PO, PO on the receiving report, receiving report on the AP voucher.
Where the chains break today: PRs raised without cost codes, deliveries received without a PO reference, and site expenses booked after the cutoff. Each one shows up later as an unexplained variance in the project profit and loss.

## Slide 11: One owner, one cycle time and one hard control for every process
Process | Trigger | Owner | Cycle time | Control that must pass
Project acquisition | Notice of award | PMO and Business Dev | 5 days, award to mobilization | Contract signed and budget opened before any PR
Purchase requisition | Approved BOM or site need | Site Engineer | 1 working day | Cost code and budget availability confirmed
Vendor and subcon award | Approved PR | Procurement | 3 to 5 working days | Three quotes and an abstract of canvass
Delivery to payment | PO issued | Warehouse and Accounting | Per PO terms, 30 days typical | PO, receiving report and invoice match
Progress billing | Monthly accomplishment cutoff | QS and Finance | 5 working days after cutoff | Joint survey signed by the client
Payroll | Semi-monthly cutoff | HR and Treasury | 3 working days after cutoff | Validated DTR and written OT approval
OPEX consolidation | Month end | Accounting | Close by day 30, report by day 5 | Coded receipts within the cutoff only
ACCOUNTABILITY SUMMARY
Cycle times are targets for the process owner, measured from the trigger to the signed output. Missed targets are reported at the weekly operations meeting with the reason and the affected project.

## Slide 12: What to confirm before this is issued as the standard process
FORMS, SYSTEMS AND NEXT STEPS
FORMS AND SYSTEM TOUCHPOINTS
Project acquisition
Billing form, invoice request, statement of accomplishment, official receipt
PMO tracker and accounting system
Material and vendor
PR form, RFQ, abstract of canvass, PO, receiving report, return to vendor slip
Procurement log and inventory module
HRIS and payroll
Manpower requisition, 201 checklist, DTR, overtime slip, payroll register, payslip
Biometrics and HRIS payroll module
OPEX
Liquidation form, expense coding sheet, budget against actual report
Accounting system and expense ledger
DECISIONS NEEDED
1. Peso limits for each approval tier
2. Billing milestones per contract type — 30/50/75/95/100 is the default here
3. Retention rate and the defects liability period
4. Payroll cutoff and release dates
5. Named owner for each of the seven acquisition steps
6. Which forms already exist in the system and which are still manual
1 CIRCULATE
2 CONFIRM LIMITS
3 ISSUE AS SOP
4 AUDIT ONE CYCLE
The flows here follow the sequence you gave: award, requisition, vendor and subcontractor award, PO, mobilization, progress billing, then invoice and receipt. Everything added — thresholds, cutoffs, retention, three-way match — is a standard construction control, shown so the team can confirm or replace it with your own rule.